## Sheet1
System Name | Hospital Management System
Members: | Miklos Kaiser A. Bolarde |  | A
| Adrian Ash D. Flores |  | B
| Geraldine D. Dela Cerna |  | C
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | October |  |  |  | Novemeber
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1.UI/UX design | All | 2024-09-24 | 2024-10-03 | Done | bar: October 1
2.Make the DataBase/Models | All | 2024-10-12 | 2024-10-13 | Done | bar: October 2
3. LOGIN | A | 2024-10-22 |  | In-Progress | bar: October 3 to October 4
3.1. Creating UI | A | 2024-10-22 |  | In-Progress | bar: October 3 to October 4
3.2. Integrate with DB | A | 2024-10-26 | 2024-10-28 | Done | bar: October 3 to October 4
4. LOGOUT | A | 2024-10-25 | 2024-10-28 | Done | bar: October 3 to October 4
5.Patient and Doctor Registration | A | 2024-10-13 |  | In-Progress | bar: October 2 to October 4
5.1. Creating UI | A | 2024-10-13 |  | In-Progress | bar: October 2 to October 4
5.2. Integrate with DB | A | 2024-10-14 | 2024-10-21 | Done | bar: October 2 to October 3
6.User Authentication | A | 2024-10-13 | 2024-10-21 | Done | bar: October 2 to October 3
7.Doctor’s Dashboard | C
8.Bed/Room Management | B | 2024-11-03 | 2024-11-07 | Done | bar: Novemeber 1
9.Equipment Usage | B
10.Billing and Invoice | B | 2024-11-03 | 2024-11-07 | Done | bar: Novemeber 1